## Project Plan
Task | Party Responsible | Skills Required | Packages and/or methodology | Status (NS/IP/C)
Develop code to read in PDF and extract information | Musonda | Python | Llama | C
Develop code to compare contracts against jursdiction amd sample risky clauses | Musonda | Python | Llama | C
Judicial Law documentation, sample contract documentation | Kevin, Yuge, Musonda | Contract Law, Linguistics |  | IP
DSPy migration | Musonda | Python | DSPy | IP
Migrate code from notebooks to .py files | Musonda | Python | Llama, DSPy | IP
Hook the user interface to the backend | Musonda | Python, HTML, CSS |  | IP
Develop code to generate "risky" clauses | Yuge, Musonda | Python, Contract Law, Linguistics | Llama | IP
Continue iteratively redefining "risky" clauses (with Prof Gillette) | Yuge, Musonda | Contract Law, Linguistics |  | IP
Develop Llama prompts to suggest changes to "risky" clauses | Kevin | Python, Prompting | Llama | IP
Develop code to output the appropriate text (i.e., a reworded clause, or judgment that a cluases is unenforceable) |  | Python |  | NS
Develop page for displaying analysis results |  | Python, HTML, CSS |  | NS
Develop Llama prompts to identify missing clauses that make contract incomplete |  | Python | Llama | NS
Expand the contract operation |  | All of the above |  | NS

## Meeting Notes - 01-20-2025
With prof gillette - Get global view of contracts - what defines ambiguity, possibly recruit law students.
Potentially include a knob to determine the level of strictness - 0 (not strict), 1 (strict)
Zero-shot prompting
hand-crafted prompting | - potentially include a filter for the different models (i.e., Kevin, Yuge, Musonda)
- in the case of numeric ambiguity - potentially highlight the issue (or add in questions)? - instead of reword, ask how much/who/which part etc?